## Est Dev Effort
ID | Title | Description | Est Dev Effort | Status
1 | User Request | Sales man make request through mobile application | 24 Hours / 3 Days
2 | Manger Approval | Managers who have privilege on integrated business solution can approve or reject any request and send notifications on email and system | 18 Hours / 2 Days
3 | Finance | Finance able to approve and reject any request | 38 Hour / 6 days
4 | Generate Document | Finance able to generate documents. | 36 Hour / 5.5 days
5 | Generate Range Number | Finance able to put range number | 21 Hour / 3 days

## DB Schema
Finance Table |  |  |  | Finance Type Table |  |  |  | Generate Number Table
ID | Column name | Type | Null | ID | Column name | Type | Null | ID | Column name | Type | Null
1 | ID PK | int | No | 1 | ID PK | int | No | 1 | ID PK | int | No
2 | Chasis Number | int | No | 2 | Type | nvarchar | No | 2 | Type | int | No
3 | Invoice Number | Int | No | 3 | Number FK | int | No | 3 | From | Int | No
4 | Traffice Note Number | int | No | 4 | Description | nvarchar | Yes | 4 | To | int | No
5 | Del | bit | No | 5 | Del | bit | No | 5 | Current | int | No
6 | CreatedDate | Date | No | 6 | CreatedDate | Date | No | 6 | CompanyCode | nvarchar | No
7 |  |  |  | 7 |  |  |  | 7 | FullName | nvarchar | Yes
8 |  |  |  | 8 |  |  |  | 8 | Del | bit | No
9 |  |  |  | 9 |  |  |  | 9 | CreatedDate | Date | No
10 |  |  |  | 10 |  |  |  | 10
Header Table |  |  |  | DetailsTable
ID | Column name | Type | Null | ID | Column name | Type | Null | SAPCompanies View
1 | ID PK | int | No | 1 | RequestID PK | int | No | ID | Column name | Type | Null
2 | Type | nvarchar | No | 2 | ChassisNumber | int | No | 1 | CompanyCode PK | int | Yes
3 | SalesOrder | Int | No | 3 | Model | nvarchar | No | 2 | CompanyName | nvarchar | Yes
4 | FullNameOfInvoice | nvarrchar | No | 4 | Brand | nvarrchar | No
5 | FullNameOFTrafficNote | nvarchar | No | 5 | TypeOfCar | nvarchar | No
6 | Address | nvarchar | No | 6 | Color | nvarchar | No
7 | CompanyCode | int | No | 7 | PlateNumber | nvarchar | No
8 | RequestDate | Date | Yes | 8 | NumberOfClynidars | Date | Yes
9 |  |  |  | 9
10 |  |  |  | 10

## User Request
ID | Title |  | Est Dev Effort
User Request
1 | Database Structure | Add new table of options types | 1
2 |  | Add new table for sales order invoice header | 1
3 |  | Add new table for sales order invoice details | 1
4 |  | Add new table for sales order invoice log | 1
5 |  | Add new table for invoice status | 1
6
7
8
9
10 | Data Validation | Empty, Mandatory , Type ,Format | 2
11 |  | Add validation of required fileds at form | 1
12
13
14
15
16
17
18 | UI Design Structure | Create new from of User request | 2
19 |  | Create new grid for chassis details | 2
20 |  | Add new tab for log and details | 2
21 |  | Add grid for History orders | 2
22 |  | Add edit function of sales order, and redirect to the form to edit entered fields | 2
23 |  | Add submit function then send it to the manager as the workflow | 2
24
25
26 | Impact | After save as draft or submit render to history tab | 1
27 |  | After submit we send mail to the manager to accpet or reject | 2
28
29
30
31
32
33
34 | Handle Exception | add exception handling at saving sales order invoice | 1
35
36
37
38
39
40
41 |  |  | 24

## Manager Approval
ID | Title |  | Est Dev Effort
Manager Approval
1 | Database Structure | Update sales order invoice status | 2
2
3
4
5
6
7
8
9
10 | Data Validation
11
12
13
14
15
16
17
18 | UI Design Structure | Add grid for pending requests | 2
19 |  | Add grid for history requests | 2
20 |  | Add grid for details of request | 2
21 |  | Add log of actions | 2
22 |  | when reject or accpet we show comment dialog to add his comment | 2
23
24
25
26 | Impact | After accpet or reject we send mail to the salesman to preview | 2
27
28
29
30
31
32
33
34 | Handle Exception
35
36
37
38
39
40
41 |  |  | 14

## Finance
ID | Title |  | Est Dev Effort
Finance
1 | Database Structure | Add New table for Finance. | 1
2 |  | Add Type column | 0.1
3 |  | Add Chassis number column | 0.1
4 |  | Add Invoice Number column | 0.1
5 |  | Add Status column | 0.1
6 |  | Add comment Column | 0.1
7 |  | add log column for every finance action. | 0.1
8
9
10 | Data Validation | Empty, Mandatory , Type ,Format | 2
11 |  | Add validation on comment format | 1
12 |  | add validation on approve | 1
13 |  | add validation on reject | 1
14 |  | add validation on SAP data | 1
15
16
17
18 | UI Design Structure | Add grid for pending request | 2
19 |  | add grid for history data | 2
20 |  | add grid for log data | 2
21 |  | add grid for detials data | 2
22 |  | add comment button | 0.3
23 |  | create pop up window for comment | 0.3
24 |  | add approve button | 0.3
|  | add reject button | 0.3
25
26 | Handle Exception | Check on pending data request | 1.5
27 |  | check on approve request | 1.5
28 |  | check on reject request | 1.5
29 |  | check old comment | 1.5
30 |  | check on save comment | 1.5
31 |  | check on save approve | 1.5
32 |  | check on log data | 1.5
33
34 | Impact | After approve send notification mail | 1
35 |  | After reject send notification mail | 1
36 |  | After approve disable reject button | 1
37 |  | Add comment for Reject only | 1
38
39
40
41
| Total |  | 31.3
37.56

## Generate Document
ID | Title |  | Est Dev Effort
Generate Document
1 | Database Structure |  | 1
2 |  |  | 0.1
3 |  |  | 0.1
4 |  |  | 0.1
5 |  |  | 0.1
6 |  |  | 0.1
7 |  |  | 0.1
8
9
10 | Data Validation | Empty, Mandatory , Type ,Format | 2
11 |  | add validation on invoice dropdownlist | 1
12 |  | add validation on tracffic note dropdownlist | 1
13 |  | add validation on date | 1
14 |  | add validation on print | 1
15 |  | add validation on Save data
16
17
18 | UI Design Structure | add invoice dropdownlist | 0.5
19 |  | add traffic note dropdownlist | 0.5
20 |  | add grid for finance | 1
21 |  | add grid for traffic note | 1
22 |  | add comment button | 0.5
23 |  | add print button | 0.5
24 |  | add save button | 0.5
|  | add datepicker for finance | 0.5
|  | add datepicker for traffic note | 0.5
|  | create teleric reprot for finance | 3
|  | create teleric reprot for invoice note | 3
25
26 | Handle Exception | Check on pending data request | 1.5
27 |  | check on approve request | 1.5
28 |  | check on reject request | 1.5
29 |  | check old comment | 1.5
30 |  | check on save comment | 1.5
31 |  | check on save approve | 1.5
32 |  | check on log data | 1.5
33
34 | Impact |  | 1
35 |  |  | 1
36
37
38
39
40
41
| Total |  | 31.6
37.92

## Generate Range Number
ID | Title |  | Est Dev Effort
Generate Range Number
1 | Database Structure | Add new Table for Range Number | 1
2 |  | Add Type Column | 0.1
3 |  | Add From Column | 0.1
4 |  | Add To column | 0.1
5 |  | Add Current Column | 0.1
6
7
8
9
10 | Data Validation | Empty, Mandatory , Type ,Format | 2
11 |  | add validation on from range number | 1
12 |  | add validation on To range number | 1
13 |  | add validation on Current range number | 1
14 |  | add validation on save data | 2
15
16
17
18 | UI Design Structure | add grid for generate range number | 2
19 |  | add save button | 0.5
20
21
22
23
24
25
26 | Handle Exception | check on From range | 1.5
27 |  | check on To range | 1.5
28 |  | check on current range | 1.5
29 |  | check on save data | 1.5
30
31
32
33
34 | Impact
35
36
37
38
39
40
41
| Total |  | 16.9
20.28

## Refrences
CashJournalLib
| GenericReports | \\fileserver\Development-Updates\SharedDLL\GenericReports.dll
| Telerik.WinControls | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
| Telerik.WinControls.ChartView | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
| Telerik.WinControls.GridView | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
| Telerik.WinControls.RichTextBox | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
| Telerik.WinControls.UI | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
| TelerikCommon | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
| TelerikData | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
CreditTreasury
| Telerik.WinControls | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
| Telerik.WinControls.GridView | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
| Telerik.WinControls.RadChart | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
| Telerik.WinControls.RadDock | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
| Telerik.WinControls.Themes.Breeze | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
| Telerik.WinControls.Themes.Desert | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
| Telerik.WinControls.Themes.Office2007Silver | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
| Telerik.WinControls.Themes.Office2010Black | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
| Telerik.WinControls.Themes.TelerikMetro | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
| Telerik.WinControls.Themes.TelerikMetroBlue | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
| Telerik.WinControls.Themes.Windows7 | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
| Telerik.WinControls.UI | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
| TelerikCommon | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
| TelerikData | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
CreditTreasuryReports
| GenericReports | \\fileserver\Development-Updates\SharedDLL\GenericReports.dll
| ReportsEngine_BLG | \\fileserver\Development-Updates\SharedDLL\ReportsEngine_BLG.dll
| ReportsEngine_Shared | \\fileserver\Development-Updates\SharedDLL\ReportsEngine_Shared.dll
| SharedDll | \\fileserver\Development-Updates\SharedDLL\SharedDll.dll
| Telerik.Reporting | C:\Program Files (x86)\Progress\Telerik Reporting R3 2017\bin\Telerik.Reporting.dll
Integration
| Telerik.WinControls | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
| Telerik.WinControls.GridView | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
| Telerik.WinControls.RadDock | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
| Telerik.WinControls.UI | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
IntegrationRpt
| GenericReports | \\fileserver\Development-Updates\SharedDLL\GenericReports.dll
| ReportsEngine_BLG | \\fileserver\Development-Updates\SharedDLL\ReportsEngine_BLG.dll
| ReportsEngine_Shared | \\fileserver\Development-Updates\SharedDLL\ReportsEngine_Shared.dll
| SharedDll | \\fileserver\Development-Updates\SharedDLL\SharedDll.dll
LegalCycle
| Telerik.WinControls | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
| Telerik.WinControls.GridView | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
| Telerik.WinControls.UI | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
| TelerikCommon | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll
| TelerikData | C:\Program Files (x86)\Telerik\UI for WinForms Q1 2015\Bin40\Telerik.WinControls.dll